## Worksheet
Startup Planning Gantt Chart (Small Business)
Task | Start Date | End Date | Duration (Days) | Status
Phase 1: Ideation
Market Research & Validation | 2025-01-05 | 2025-01-19 | 14
Define Value Proposition | 2025-01-13 | 2025-01-23 | 10
Phase 2: Planning
Business Model Design | 2025-01-16 | 2025-01-31 | 15
Develop MVP Scope | 2025-01-20 | 2025-02-03 | 14
Phase 3: Development
Build MVP Prototype | 2025-01-31 | 2025-03-14 | 44
MVP Launch (Beta Testing) | 2025-03-14 | 2025-03-14 | 1
Phase 4: Launch & Growth
Customer Acquisition Campaign | 2025-03-15 | 2025-04-30 | 46
Initial Funding Round | 2025-03-25 | 2025-04-15 | 21
Phase 5: Scaling (Q2)
Expand Product Features | 2025-04-16 | 2025-06-30 | 75
* This Gantt Chart is a visual representation of the startup planning timeline. Progress percentages indicate task completion status.