## Worksheet
Startup Planning - Gantt Chart (Summary View)
Task ID | Task Name | Start Date | End Date | Durations (Days) | Status
1 | Market Research | 2024-01-05 | 2024-01-25 | 21 | In Progress
1.1 | Market Validation Complete | 2024-01-25 | 2024-01-25 | 0 | Completed
2 | Product Design & Prototyping | 2024-01-30 | 2024-03-15 | 45 | In Progress
2.1 | Prototype Ready for Testing | 2024-03-15 | 2024-03-15 | 0 | In Progress
3 | Full Product Development | 2024-03-18 | 2024-05-15 | 60 | To Do
3.1 | Beta Version Complete | 2024-05-15 | 2024-05-15 | 0 | To Do
4 | Go-to-Market Strategy & Marketing Setup | 2024-05-18 | 2024-06-30 | 45 | To Do
4.1 | Launch Readiness Review Complete | 2024-06-30 | 2024-06-30 | 0 | To Do
5 | Official Product Launch & Initial Campaigns | 2024-07-03 | 2024-07-14 | 12 | To Do
5.1 | Product Launch Complete (Day 1) | 2024-07-03 | 2024-07-03 | 0 | To Do
Total Project Duration: |  |  |  | 183 days
Note: Dates are based on a standard calendar year, excluding weekends and holidays.