## Worksheet
Startup Planning - Gantt Chart (Team Use)
Task / Milestone | Start Date | End Date | Duration (Days) | Owner | Status | Progress
Phase 1: Concept & Validation
Market Research | 2024-04-01 | 2024-04-15 | 15 | Alice Chen | In Progress
User Persona Development | 2024-04-16 | 2024-04-30 | 15 | Brian Kim | In Progress
Competitor Analysis | 2024-05-01 | 2024-05-15 | 15 | Claire Thompson | Pending
Phase 2: Product Development
Product Wireframing | 2024-05-16 | 2024-06-15 | 31 | Alice Chen | Pending
UI/UX Design Finalization | 2024-06-16 | 2024-07-15 | 30 | Brian Kim | Pending
Phase 3: Team & Launch Preparation
Hiring Key Roles (Dev, PM) | 2024-07-16 | 2024-08-15 | 31 | Claire Thompson | Pending
Product MVP Ready | 2024-08-15 | 2024-08-15 | - | All Team Members | Milestone Achieved
Phase 4: Launch & Feedback
Soft Launch to Beta Users | 2024-08-16 | 2024-09-15 | 31 | Alice Chen | Pending
Full Public Launch | 2024-09-16 | 2024-09-16 | - | All Team Members | Milestone Pending
Total Timeline | 2024-04-01 | 2024-09-16 | 199 Days
Legend:
● Progress Bar- Current progress of task
Phase Header- Phase grouping
Milestone- Key achievement point