## Worksheet
Startup Planning - Gantt Chart Template (Version 1.0)
Task / Activity | Start Date | End Date | Duration (Days) | Progress (%)
Phase 1: Ideation
Market Research & Validation | 2023-10-01 | 2023-10-15 | 15 | 85%
Competitor Analysis | 2023-10-16 | 2023-10-25 | 10 | 75%
Define Core Value Proposition | 2023-10-26 | 2023-11-05 | 10 | 95%
Phase 2: Business Model Development
Design Business Model Canvas | 2023-11-06 | 2023-11-15 | 10 | 80%
Revenue Stream Planning | 2023-11-16 | 2023-11-25 | 10 | 70%
Cost Structure Analysis | 2023-11-26 | 2023-12-05 | 10 | 90%
Phase 3: MVP Development
Define MVP Scope | 2023-12-06 | 2023-12-15 | 10 | 95%
UI/UX Design | 2023-12-16 | 2024-01-15 | 30 | 75%
Frontend Development | 2024-01-16 | 2024-02-15 | 31 | 65%
Backend Development | 2024-01-16 | 2024-03-15 | 60 | 55%
Testing & QA | 2024-03-16 | 2024-04-15 | 31 | 35%
Phase 4: Launch Preparation
Marketing Strategy & Content | 2024-03-16 | 2024-05-15 | 61 | 45%
Legal & Compliance Setup | 2024-03-16 | 2024-05-15 | 61 | 75%
Seed Funding Pitch Deck | 2024-04-01 | 2024-05-15 | 45 | 95%
Milestone: MVP Complete | 2024-04-15 | 2024-04-15 | 0
Milestone: First Beta Users (100) | 2024-06-30 | 2024-06-30 | 0
Milestone: Official Launch (Version 1.0) | 2024-12-31 | 2024-12-31 | 0
Total Timeline Duration: | Approx. 785 Days (Oct 2023 – Dec 2024)
Template Version: 1.0 ¦ Created for Startup Planning ¦ Designed to mimic Excel Gantt Chart layout