## Worksheet
Startup Planning - Home Template - Data Version
Phase | Key Activity | Responsible Team | Due Date | Status | Milestone Achieved?
Market Research & Validation
Phase 1 | Conduct target market analysis | Product Team | 2023-10-31 | In Progress | No
Phase 1.1 | Identify customer pain points through surveys | Marketing Team | 2023-10-25 | Completed | Yes
Phase 1.2 | Analyze competitive landscape | Strategy Team | 2023-10-30 | In Progress | No
Product Development
Phase 2 | Design MVP (Minimum Viable Product) | Product Team | 2023-11-15 | Pending | No
Phase 2.1 | Create wireframes and UI mockups | Design Team | 2023-11-05 | In Progress | No
Phase 2.2 | Develop core functionality prototype | Engineering Team | 2023-11-14 | Pending | No
Go-to-Market Strategy
Phase 3 | Define pricing model and monetization strategy | Finance Team | 2023-11-20 | Pending | No
Phase 3.1 | Conduct pricing sensitivity analysis | Data Analytics Team | 2023-11-10 | Pending | No
Phase 3.2 | Develop launch campaign and messaging framework | Marketing Team | 2023-11-18 | Pending | No
Total Tasks: |  |  |  | 12 | 3 / 12 completed