## Worksheet
Startup Planning - Home Template (Extended)
Phase | Key Activities | Responsible Team | Status | Start Date | End Date | Budget (USD) th>
Market Research & Validation | Conduct surveys, interviews, and competitive analysis. | Product & Market Team | In Progress | 2024-03-01 | 2024-03-15 | 15,000
Business Model Development | Create value proposition, revenue streams, and cost structure. | Strategy & Finance Team | Not Started | 2024-03-16 | 2024-03-31 | 8,500
Product Design & Prototyping | Develop wireframes, mockups, and MVP prototype. | Design & Engineering Team | Pending | 2024-04-01 | 2024-05-15 | 35,000
Funding & Investor Outreach | Prepare pitch deck, investor outreach, and funding rounds. | Founder & Finance Team | Not Started | 2024-05-16 | 2024-06-30 | 12,000
Team Building & Hiring | Recruit core team members, define roles and onboarding. | HR & Leadership Team | Pending | 2024-06-01 | 2024-07-31 | 55,000
Launch Preparation & Marketing | Create go-to-market strategy, website, social media campaigns. | Marketing & Product Team | Pending | 2024-08-01 | 2024-08-31 | 30,500
Official Product Launch | Release MVP to early adopters, monitor feedback. | Entire Team | Pending | 2024-09-01 | 2024-09-30 | 18,750
Total Estimated Budget: | [5 empty] | 174,750
Notes:
This template is designed for extended startup planning with detailed phase tracking.
Adjust dates, responsibilities, and budgets as needed during execution.
Status indicators: Not Started / Pending / In Progress / Completed.