## Worksheet
Startup Planning - Quarterly Home Template
Quarter | Key Objectives | Milestones & Deliverables | Responsible Team/Person | Status (Progress) | Notes / Risks
Q1: January - March
Q1 | Finalize business model and value proposition | Complete customer personas, revenue model, MVP wireframes | Product & Strategy Team | In Progress (60%) | Delayed due to stakeholder feedback cycle.
Q2: April - June
Q2 | Build MVP and conduct initial user testing | MVP development, beta testing with 50 users, usability report | Engineering & UX Team | Not Started (0%) | Need to secure additional dev resources.
Q3: July - September
Q3 | Leverage early feedback to iterate and scale MVP | Enhanced features, onboarding flow update, launch to 200 users | Product & Growth Team | Not Started (0%) | Risk: User adoption lower than expected in Q2.
Q4: October - December
Q4 | Secure Series A funding and expand core team | Funding pitch deck, investor meetings, hire 3 key roles | CEO & Finance Team | Not Started (0%) | Market conditions may delay fundraising timeline.
Total Progress |  | In Progress: 20% (1/5 objectives completed)