## Worksheet
Startup Planning - Monthly Planner (Data Version)
Date | Week | Objective | KPI Target | Status | Budget Allocated ($) | Budget Spent ($) | Revenue Projection ($) | Actual Revenue ($) | Team Tasks | Risk Level | Action Items
Week 1: Planning & Setup (01-07)
Jan 02 | Wk 1 | Finalize MVP Features | 8/8 Features Defined | Pending | 5,000 | 1,200 | 25,000 | 18,456Create wireframes; Assign devs; Set deadlines | Medium | Add feedback loop to dev team by Jan 5
Jan 04 | Wk 1 | Hire Key Developers (2) | 2 Hires Completed | In Progress | 8,000 | 3,500 | 35,00012,678Candidate screening; Conduct interviews; Send offers | High | Finalize onboarding kit by Jan 6
Jan 07 | Wk 1 | Weekly Review Meeting | Review progress, adjust goals, assign new tasks
Week 2: Development Kickoff (08-14)
Jan 09 | Wk 2 | Begin MVP Coding Phase | Start backend & frontend development in parallel | [6 empty] | Medium
Jan 14 | Wk 2 | Mid-Week Sprint Check-in ¦ Update KPIs and timelines
Week 3: Prototype & Testing (15-21)
Jan 17 | Wk 3 | Build MVP prototype version; Initiate internal QA testing | [8 empty] | Medium
Jan 21 | Wk 3 | Beta Test Phase Begins ¦ Collect feedback from internal users
Week 4: Review & Launch Readiness (22-31)
Jan 25 | Wk 4 | Refine MVP based on feedback; Finalize UI/UX improvements | [8 empty] | Low
Jan 28 | Wk 4 | Final Pre-Launch Review ¦ Approve launch date & marketing plan
Monthly Summary: |  |  | 10/12 Objectives Completed | 45% Progress | $25,000 | $9,200$95,876Risk: Medium ¦ Action: Monitor development velocity weekly.