## Worksheet
Startup Planning - Monthly Planner (Manager View)
Date | Key Objectives |  |  | Progress Status |  | Team Members | Manager Notes
| Objective Description | Target Completion Date | KPIs / Deliverables | Progress (%) | Status Indicator
Product Development Phase - Q3 Roadmap
2023-09-05 | Finalize MVP features list | 2023-10-15 | List of 15 core features with priority ranking | 85% | 🟢 On Track | Dev Team, Product Lead | Feature prioritization aligned with customer feedback surveys.
2023-09-15 | Complete UI/UX wireframes for key screens | 2023-10-10 | High-fidelity mockups for onboarding, dashboard, settings | 75% | 🟡 At Risk | UX Designer, Frontend Dev | Minor delays due to stakeholder feedback loop.
Team & Operations Planning
2023-09-20 | Hire senior backend developer | 2023-10-31 | Confirmed offer acceptance and onboarding completion | 50% | 🟡 At Risk | Talent Acquisition, CTO | Competitive market for talent; extending timeline slightly.
2023-09-25 | Establish weekly stand-up framework | 2023-10-15 | Standardized meeting template and time slot defined | 100% | 🟢 On Track | All Departments | Adopted across teams with positive feedback.
Financial & Investor Updates
2023-09-30 | Prepare Q3 financial report & investor deck | 2023-11-15 | Fully audited financials and 8-slide pitch presentation | 60% | 🟡 At Risk | Finance Lead, CEO | Delayed due to internal audit review; on track for extension.
Marketing & Customer Acquisition
2023-10-10 | Launch pre-launch landing page campaign | 2023-10-31 | Campaign reaching 5,000+ leads with 5% conversion rate | 45% | 🟡 At Risk | Marketing Team, Growth Lead | Initial engagement lower than expected; optimizing ad creatives.
Monthly Summary & Planning Review
2023-10-31 | Conduct monthly performance review meeting | 2023-11-05 | Memo summarizing progress, challenges, and next month's goals | 0% | 🔴 Not Started | CEO & Management Team | Pending; scheduled for Nov 5th. Must prioritize.
Manager's Comments: Overall progress is solid with a few risks in hiring and marketing. Key focus areas for October: accelerate product design, finalize recruitment, and improve lead conversion rates. Ensure all review meetings are conducted on time.