## Worksheet
Startup Planning - Monthly Overview
Month: January ¦ Year: 2024
Date | Milestone / Objective | Status | Responsible Team Member | Notes & Actions
No entries yet. Add key milestones for the month.
Key Performance Indicators (KPIs)
KPI | Target | Actual | Status
New User Acquisition | 500 | -- | Pending Update
Conversion Rate (Trial to Paid) | 15% | -- | Pending Update
Total Revenue (MRR) | $10,000 | -- | Pending Update
Page 1 of 4 ¦ Startup Planning - Monthly Planner
Startup Planning - Weekly Breakdown
Month: January ¦ Year: 2024
Week | Key Activities & Goals | Budget Allocation (USD) | Risks / Challenges
Week 1 (Jan 1–7) | Finalize MVP features, onboard first beta users | $3,000 | Limited developer bandwidth
Week 2 (Jan 8–14) | Collect user feedback, prioritize feature updates | $2,500 | Bug reports delaying release timeline
Week 3 (Jan 15–21) | Launch beta campaign, run social ads | $6,000 | Ad spend exceeding target if not optimized
Week 4 (Jan 22–31) | Review analytics, plan Q1 roadmap | $4,500 | Data insights delayed due to system lag
Team Availability & Resource Summary
Role/Department | Full-Time Staff | Part-Time/Contractors | Total Capacity (hrs/wk)
Product & Development | 4 | 2 | 160
Sales & Marketing | 3 | 1 | 96
Customer Support | 2 | 0 | 80
Total Resources:Page 2 of 4 ¦ Startup Planning - Monthly Planner
Startup Planning - Financial & Budget Tracker
Month: January ¦ Year: 2024
Category | Budgeted (USD) | Actual (USD) | Variance
Marketing & Ads | $12,000 | -- | --
Salaries & Benefits | $45,000 | -- | --
Software & Tools (SaaS) | $3,200 | -- | --
Office & Utilities | $1,800 | -- | --
Total Expenses:
Monthly Burn Rate Analysis
Metric | Value (USD) | Status | Action Required?
Current Monthly Burn Rate | $62,000 | High Risk | Yes - Optimize marketing spend
Funds Available (Cash Runway) | $248,000 (4 months) | Low Confidence | No - Monitor weekly
Page 3 of 4 ¦ Startup Planning - Monthly Planner
Startup Planning - Action Items & Meeting Log
Month: January ¦ Year: 2024
Date of Action | Action Item | Prioritized (Y/N) | Owner | Status | Due Date
Jan 3, 2024 | Finalize MVP roadmap with product team | Y | C. Johnson (PM) | In Progress
Jan 5, 2024 | Schedule investor demo for next week | Y | M. Lee (CEO)
Upcoming Meetings: Jan 10 (Team Sync), Jan 17 (Board Review), Jan 24 (Product Demo)
Key Decisions Made This Month
Decision:Prioritize user onboarding improvements over new feature development.
Decision:Shift ad budget from Facebook to Google Ads based on higher conversion rates.
Decision:Hire one additional full-stack developer to handle backlog.