## Worksheet
Startup Planning - Monthly Planner (Planning View)
Week | Mon | Tue | Wed | Thu | Fri | Sat | Sun
Week 1 01-07 Apr | Team onboarding Project kickoff | Market research review Competitor analysis | Product roadmap planning Feature prioritization | Design sprint initiation Wireframe creation | Feedback collection Stakeholder meeting
Week 2 - 08-14 Apr
| Prototype development UI/UX refinement | Technical architecture review Server setup | API design session Data model planning | Development sprint 1 start Codebase initialization | Backlog grooming Sprint planning meeting
Week 3 - 15-21 Apr
| Sprint progress review Task tracking | User testing prep Test scenario design | Content strategy development Blog planning | Sales funnel optimization Landing page update | Investor pitch deck update Financial modeling check
Week 4 - 22-30 Apr
Beta release preparation Quality assurance check | Feedback analysis Feature adjustments | Marketing campaign launch Social media schedule | Customer onboarding process Support system setup | Monthly performance review KPI tracking
Monthly Summary: Key Achievements & Next Steps
Notes:Customize tasks per startup phase. Use color coding for task status (e.g., green = done, yellow = in progress, red = delayed).