## Worksheet
Startup Planning - Quarterly Monthly Planner
Month | Key Objectives & Goals |  |  | Financial Targets |  | Team & Resources
| Strategic Initiative | Key Metrics (KPIs) | Action Steps | Budget Allocation ($) | Revenue Target ($)
Q1: January – March 2025
January | Finalize MVP design and user flow | User sign-ups: 500 Feedback rate: 80% | Design sprint, UX testing, wireframes approved | 25,000 | 15,000 | 3 designers 1 product manager
February | Begin development of core features | Feature completion: 40%Bug rate: <1% | Agile sprints, code reviews, CI/CD setup | 35,000 | 22,500 | 6 developers 1 QA engineer
March | Soft launch to beta users; gather feedback | Beta user count: 1,000 Retention (30-day): 45% | Pilot program, feedback survey rollout, iterate | 20,000 | 35,000 | 2 marketers 1 customer support rep
Q2: April – June 2025
April | Refine MVP based on beta feedback | User satisfaction (NPS): ≥70 Bug fixes: 100% | Feedback analysis, redesigns, bug tracking | 28,000 | 45,000 | 3 developers 1 UX specialist
May | Landing page & marketing campaign launch | Campaign reach: 50K Conversion rate: 3.5% | Social media ads, SEO, email funnel setup | 40,000 | 65,000 | 2 marketers 1 copywriter
June | Pilot sales & customer onboarding process test | Onboarding completion: 85% CAC: $35 | Onboarding flow, CRM integration, support training | 30,000 | 85,000 | 1 sales lead 2 support staff 1 ops manager
Q3: July – September 2025
July | Full public launch with v1.0 release | Monthly active users: 5,000 User churn: <8% | Promotional campaign, influencer outreach, PR | 50,000 | 125,000 | Full team + 1 community manager
August | Introduce first premium tier & pricing model | Premium conversion: 5% LTV increase: 30% | Pricing strategy, feature gating, payment system integration | 25,000 | 180,000 | Product team Finance analyst
September | Gather user insights & plan v2.0 features | User survey completion: 90% Feature backlog: 15 items | Analytics review, roadmap planning, stakeholder sync | 15,000 | 225,000 | All departments Focused workshop session
Q4: October – December 2025
October | Launch v2.0 with major performance upgrade | App load time: <1.5s Critical bugs: 0 | Performance optimization, testing, rollout plan | 45,000 | 275,000 | Developers SysOps team
November | Growth & retention campaign during holiday season | User growth: 30% LTV increase: 25% | Holiday promo, referral program, email drip campaigns | 60,000 | 350,000 | Marketing team Sales enablement lead
December | Year-end review & 2026 planning kickoff | Q4 KPIs met: 100% Roadmap approved for Q1 2026 | Performance report, stakeholder meeting, strategy retreat | 35,000 | 450,000 | Executive team All department heads
Total (Q1–Q4) | Strategic milestones achieved: 12/12 |  | Key feature deliveries: 5 | 308,000 | 1,975,000 | Team size: Avg. 14 members
This planner template supports startup quarterly planning with actionable monthly targets, financial goals, and team alignment.