## Worksheet
Startup Monthly Planner - Team Use
Team Member | Goals & Objectives |  |  | Key Tasks & Deliverables |  |  |  | Status | Owner(s)
| Priority Level | Target Date | Description | Due Date | Status Update (Weekly) | Action Items | Milestones Achieved
John Doe - Product Lead | High | 2024-06-30 | Finalize MVP feature set and user flow design. | 2024-06-15 | Completed initial wireframes; feedback collected from UX team. | Create prototype for stakeholder review. | No | John Doe, Sarah Kim
Jane Smith - Dev Manager | High | 2024-07-10 | Begin backend API development for core user authentication. | 2024-06-30 | Scaffolded project structure; defined data models. | Implement JWT-based login system by June 25. | No | Jane Smith, Alex Rivera
Mike Chen - Marketing Lead | Medium | 2024-07-15 | Promote beta launch via social media and email campaigns. | 2024-07-15 | Campaigns drafted; scheduled for June 28 release. | Design landing page and teaser video content. | No | Mike Chen, Lisa Tran
Sarah Kim - UX Designer | High | 2024-06-25 | Complete usability testing for v1.0 prototype. | 2024-06-18 | User tests conducted with 8 participants; insights compiled. | Share findings and revise interface based on feedback. | Yes | Sarah Kim, John Doe
Alex Rivera - Full Stack Developer | High | 2024-07-05 | Develop and test real-time chat functionality. | 2024-07-15 | Draft architecture plan; integrated WebSocket library. | Fully implement and QA chat module by July 3. | No | Alex Rivera, Jane Smith
Total Items: |  |  |  |  | Completed: 1 ¦ In Progress: 4 ¦ Not Started: 0 |  |  | Monthly Review Date: June 28, 2024