## Worksheet
Startup Planning - Advanced Planner Template
Phase | Key Activities | Timeline (Weeks) | Owner(s) | Status | Budget Allocated ($)
1. Market Research & Validation
Research | Conduct customer interviews, competitive analysis, and market sizing | Weeks 1-4 | Product Manager, Market Analyst | In Progress | $5,000
Validation | Create MVP concept, run landing page test, collect early sign-ups | Weeks 5-6 | Founder, Growth Lead | Pending | $3,000
2. Product Development & Design
Design | Wireframing, UI/UX prototyping, design system creation | Weeks 7-9 | Lead Designer, UX Researcher | Pending | $8,000
Development | Frontend & backend development, API integration, testing cycles | Weeks 10-18 | CTO, Engineering Team | Pending | $45,000
3. Business Model & Fundraising Strategy
Model Design | Define revenue streams, pricing strategy, scalability plan | Weeks 19-20 | Founder, CFO | Pending | $2,500
Funding Prep | Prepare pitch deck, financial projections, investor outreach plan | Weeks 21-23 | CFO, Founder | Pending | $4,000
4. Go-to-Market & Growth Strategy
Pre-Launch | Build waitlist, run beta tests, finalize onboarding flow | Weeks 24-25 | Growth Lead, Product Manager | Pending | $6,000
Launch Campaign | Execute marketing campaigns, PR outreach, partner integrations | Weeks 26-30 | Marketing Director, Sales Lead | Pending | $20,000
Total Projected Budget: |  |  |  |  | $93,500
Notes:
- All timeline estimates are flexible based on feedback and iteration cycles.
- Budgets are preliminary and subject to reallocation during execution.