## Worksheet
Item | Description | Target Date | Status | Responsible Person
Business Idea Validation | Define and validate the core business concept with market research. | 2023-10-31 | Not Started | John Doe
Market Research & Analysis | Conduct competitor analysis and identify target customer segments. | 2023-11-15 | Not Started | Jane Smith
Business Model Canvas | Draft the business model using the canvas framework. | 2023-11-30 | Not Started | Alex Johnson
Team Formation | Identify and onboard key team members. | 2023-12-15 | Not Started | Sarah Lee
Funding Strategy | Develop pitch deck and identify potential funding sources. | 2023-12-31 | Not Started | Mike Brown
Prototype Development | Create MVP or prototype based on validated idea. | 2024-01-31 | Not Started | Emma Wilson
Customer Feedback Loop | Test prototype with early users and collect feedback. | 2024-02-15 | Not Started | David Martinez
Go-to-Market Strategy | Define launch plan, channels, and marketing approach. | 2024-03-15 | Not Started | Lisa Garcia
Launch Preparation | Finalize legal, financial, and operational setup. | 2024-03-31 | Not Started | Robert Taylor
Official Launch | Release product/service to public market. | 2024-04-30 | Not Started | All Team Members