## Worksheet
Startup Planning - Business Use Planner Template
Phase | Key Activity | Timeline (Weeks) | Status | Responsible Person | Milestones & Deliverables
Concept Development | Define business idea, value proposition, and target market. | 1–4 | Pending | Jane Smith (CEO) | Business concept document completed.
Market Research | Conduct surveys, competitor analysis, and customer interviews. | 3–6 | Pending | Mark Lee (Marketing Lead) | Comprehensive market analysis report.
Business Model Design | Create revenue streams, cost structure, and key partnerships. | 4–7 | Pending | Alice Johnson (COO) | Business model canvas finalized.
Financial Planning | Develop 3-year financial projections, budget, and funding plan. | 5–9 | Pending | David Brown (CFO) | Income statement, cash flow forecast, balance sheet.
Legal & Compliance | Select business entity, register trademarks, draft contracts. | 6–10 | Pending | Sarah Wilson (Legal Counsel) | Entity registered and legal documentation archived.
Prototype Development | Build MVP or prototype based on feedback and feasibility. | 7–12 | Pending | Tom Reed (CTO) | MVP version 1.0 delivered and tested.
Go-to-Market Strategy | Launch marketing campaign, pricing strategy, sales channels. | 10–14 | Pending | Lisa Chen (Growth Lead) | Marketing launch plan and first campaign executed.
Team Formation | Hire core team, define roles, onboard employees. | 8–16 | Pending | Jane Smith (CEO) | Full founding team hired and integrated.
Launch & Scale | Official product launch, gather user feedback, iterate. | 15–20 | Pending | Executive Team | Product live in market with 100+ early users.