## Startup Planning - Data Version
Phase | Key Activity | Responsible Team Member | Start Date | End Date | Status | Budget Allocation ($)
Market Research & Validation | Conduct customer interviews, analyze market trends, validate problem-solution fit | Product Manager | 2024-01-15 | 2024-03-31 | In Progress | 7,500
Product Development (MVP) | Design wireframes, develop minimum viable product, conduct alpha testing | Engineering Team Lead | 2024-04-01 | 2024-07-31 | Pending | 55,000
Business Model Design | Create revenue model, pricing strategy, go-to-market plan | CEO & Finance Lead | 2024-04-15 | 2024-06-30 | In Progress | 8,500
Funding Round Preparation | Develop pitch deck, financial projections, investor outreach materials | Founder & CFO | 2024-06-01 | 2024-08-31 | Pending | 15,000
Alpha Testing & Feedback Loop | Recruit beta users, collect feedback, iterate on product features | Product Manager & UX Designer | 2024-08-01 | 2024-10-31 | Pending | 9,500
Go-to-Market Launch | Execute marketing campaign, onboard first customers, monitor KPIs | Marketing Lead & Sales Director | 2024-11-01 | 2025-01-31 | Pending | 45,000
Total | [6 empty] | 140,500