## Worksheet
Startup Planning - Detailed Planner Template
Phase | Activity/Task | Description | Responsible Person | Status | Due Date | Budget Allocated ($)
Phase 1: Ideation & Concept Development
Phase 1 | Market Research | Analyze industry trends, customer needs, and competitor landscape. | Marketing Lead | In Progress | 2025-04-15 | 3,500.00
Phase 1 | Define Core Value Proposition | Create a clear statement of unique value for customers. | Founder | Pending | 2025-04-10 | 1,000.00
Phase 2: Business Model & Strategy Design
Phase 2 | Develop Business Model Canvas | Complete all nine blocks of the canvas (Customer Segments, Revenue Streams, etc.). | Strategy Manager | In Progress | 2025-04-20 | 1,500.00
Phase 2 | Create Go-to-Market Strategy | Outline sales channels, pricing model, and customer acquisition plan. | Sales Director | Pending | 2025-04-18 | 2,000.00
Phase 3: Product & Technology Development
Phase 3 | Build MVP (Minimum Viable Product) | Develop core product features based on validated requirements. | Lead Developer | Pending | 2025-05-10 | 15,000.00
Phase 3 | User Testing & Feedback Loop | Conduct usability tests with target users and collect feedback. | UX Researcher | Pending | 2025-05-15 | 3,000.00
Phase 4: Team Building & Operational Setup
Phase 4 | Hire Key Personnel | Recruit core team members (dev, marketing, operations). | HR Manager | Pending | 2025-04-30 | 45,000.00
Phase 4 | Set Up Legal Structure & IP Protection | Register company, obtain trademarks, and draft NDAs. | Legal Advisor | Pending | 2025-04-25 | 8,000.00
Phase 5: Fundraising & Pre-Launch Preparation
Phase 5 | Prepare Pitch Deck & Financial Model | Create investor-ready materials including financial projections. | CFO/Founder | Pending | 2025-04-28 | 4,000.00
Phase 5 | Secure Seed Funding Round | Pitch to investors and close funding of $250K. | Founder/CEO | Pending | 2025-06-15 | 10,000.00
Total Estimated Budget: | [5 empty] | $107,000.00