## Worksheet
Task | Owner | Start Date | End Date | Status | Priority | Budget (USD)
Market Research & Analysis | Jane Doe | 2024-01-05 | 2024-01-25 | In Progress | High | $8,500
Business Model Development | John Smith | 2024-01-15 | 2024-01-31 | To Do | High | $5,000
Prototype Design & Development | Alex Johnson | 2024-01-20 | 2024-03-15 | To Do | High | $35,000
Funding Strategy & Pitch Deck Creation | Sarah Lee | 2024-01-28 | 2024-03-10 | In Progress | High | $7,500
Legal & Regulatory Setup | Michael Brown | 2024-02-01 | 2024-03-31 | To Do | Medium | $15,000
Hiring Core Team Members | Lisa Garcia | 2024-03-15 | 2024-04-30 | To Do | High | $60,000
User Testing & Feedback Collection | David Kim | 2024-04-15 | 2024-05-31 | To Do | Medium | $18,000
Go-to-Market Strategy Finalization | Jennifer White | 2024-05-15 | 2024-06-15 | To Do | High | $12,000
Launch Campaign Planning & Execution | Taylor Evans | 2024-06-15 | 2024-07-31 | To Do | High | $45,000