## Startup Planning - Manager View
Startup Planning - Manager View
Phase | Key Objective | Status | Owner | Dates (Start - End) | Budget Allocated ($)
Phase 1: Ideation & Market Validation
Market Research | Define target market and validate problem-solution fit | In Progress | Jane Doe | 2024-04-01 - 2024-04-15 | 5,000
Competitor Analysis | Map key competitors and identify differentiation opportunities | Completed | John Smith | 2024-04-16 - 2024-04-30 | 3,500
Phase 2: Product Development & MVP Build
Product Design | Create wireframes and UX prototypes for core features | In Progress | Alice Johnson | 2024-05-01 - 2024-06-15 | 8,000
MVP Development | Develop minimum viable product with core functionality | Not Started | Mike Wilson | 2024-06-16 - 2024-08-31 | 35,000
Phase 3: Go-to-Market & Launch Preparation
Marketing Plan | Develop digital marketing and customer acquisition strategy | In Progress | Sarah Brown | 2024-06-01 - 2024-07-31 | 7,500
Customer Onboarding Flow | Create seamless onboarding experience for new users | Not Started | David Lee | 2024-08-01 - 2024-08-31 | 6,500
Phase 4: Launch & Scaling Strategy
Soft Launch (Pilot) | Test with 500 early users and collect feedback | Not Started | Lisa Garcia | 2024-09-15 - 2024-10-31 | 15,000
Scaling Plan (Q4) | Create roadmap for user acquisition and revenue growth | Not Started | Robert Taylor | 2024-10-01 - 2024-12-31 | 18,500
Total Budget Allocated: |  |  |  |  | $103,000