## Worksheet
Startup Planning - Planner Template
Planning View ¦ Template Type: Planner Template ¦ Purpose: Startup Planning
Phase | Key Activities | Responsible Person | Timeline (Start - End) | Status | Milestones & Deliverables
Discovery & Ideation | Market research, customer interviews, problem validation, solution brainstorming | CEO / Product Manager | Jan 2025 - Feb 2025 | In Progress | Validated problem statement, initial MVP concept document
Business Model Development | Business model canvas, revenue streams analysis, cost structure planning | CTO / CFO | Mar 2025 - Apr 2025 | Not Started | Completed business model canvas, financial projections Q1-Q4 2025
Product Development (MVP) | Wireframing, UI/UX design, frontend/backend development, testing | CTO / Engineering Team | May 2025 - Aug 2025 | In Progress | MVP prototype, internal testing report, user feedback summary
Go-to-Market Strategy | Marketing plan, sales funnel design, pricing strategy, channel selection | CPO / Marketing Lead | Sep 2025 - Oct 2025 | Not Started | Go-to-market launch plan, customer acquisition strategy document
Fundraising Preparation | Investor pitch deck, financial model refinement, term sheet review | CEO / CFO | Nov 2025 - Dec 2025 | In Progress | Pitch deck v4.1, investor outreach list, term sheet negotiation framework
Launch & Growth Phase | Public launch, user acquisition campaigns, performance monitoring | Marketing / Sales Team | Jan 2026 - Mar 2026 | In Progress | First 1,000 paying users, initial KPI dashboard setup
Last updated:April 5, 2025