## Worksheet
Startup Planning - Quarterly Planner
Template Type:Planner Template ¦Style/Version:Quarterly ¦Purpose:Startup Planning
Quarter | Key Objectives & Goals |  |  |  | Milestones & Deliverables |  |  |  | Owner | Status
| Objective 1 | Objective 2 | Objective 3 | Objective 4 | Milestone A | Milestone B | Milestone C | Milestone D
Q1: Jan - Mar 2025
Strategic Focus: Product Development & Market Research
| Finalize MVP features and user flow |  |  |  | Complete wireframes and prototypes | Conduct initial user testing (50+ participants) | Pilot version released to beta testers | Evaluate feedback for iteration plan | Dev Team Lead | In Progress
| Complete market analysis and competitor benchmarking |  |  |  | Finalize target customer personas | Identify key differentiators vs. competitors | Presentation to founding team approved |  | Market Research Lead | In Progress
Q2: Apr - Jun 2025
Strategic Focus: MVP Launch & Early User Acquisition
| Launch MVP on web and mobile platforms |  |  |  | Complete final QA and security audit | Deploy to App Store and Google Play | Onboard first 1,000 users within 30 days | Gather initial engagement metrics (DAU/MAU) | Product Manager | Delayed
| Build foundational marketing strategy |  |  |  | Create content calendar for first 3 months | Launch social media channels (LinkedIn, Twitter) | Run first paid campaign (Google Ads & Meta) | Acquire 500 qualified leads | Marketing Lead | In Progress
Q3: Jul - Sep 2025
Strategic Focus: User Growth & Feedback Integration
| Improve product based on user feedback |  |  |  | Implement top 5 requested features | Optimize onboarding experience | Reduce churn rate by 15% | Evaluate retention through cohort analysis | Product Team | Completed
| Expand marketing efforts to new channels |  |  |  | Launch influencer partnership program | Begin email marketing automation setup | Grow user base to 5,000 active users | Generate $10K in pilot revenue from premium features | Growth Manager | In Progress
Q4: Oct - Dec 2025
Strategic Focus: Scaling & Investor Readiness
| Prepare for Series A funding round |  |  |  | Complete financial projections through 2027 | Finalize pitch deck and investor materials | Secure 3 pilot enterprise clients | Reach $50K MRR target by year-end | Funding & Strategy Lead | Delayed
| Strengthen internal processes and team structure |  |  |  | Hire key roles: CTO, Head of Sales | Implement OKR system across departments | Conduct mid-year performance reviews | Evaluate tech stack for scalability | HR & Operations Lead | In Progress
Note: This template can be customized for specific startup goals and timelines. Status updates should be reviewed monthly.