## Worksheet
Startup Planning - Report Version
Phase | Objective | Key Activities | Timeline (Est.) | Status | Responsible Party
Phase 1: Concept & Ideation
1.1 | Define Core Business Idea | Conduct market gap analysis, brainstorm value propositions, finalize unique selling proposition (USP). | Weeks 1–2 | In Progress | CEO & Co-Founder
1.2 | Validate Market Need | Survey target customers, conduct interviews, analyze competitor offerings. | Weeks 3–4 | Pending | Marketing Lead
Phase 2: Planning & Strategy
2.1 | Develop Business Model Canvas | Map out key partners, activities, customer segments, revenue streams. | Weeks 5–6 | Pending | Strategy Team
2.2 | Create Financial Projections (12-Month) | Forecast revenue, expenses, cash flow, break-even analysis. | Weeks 7–8 | Pending | Finance Lead
Phase 3: Development & Setup
3.1 | Build MVP (Minimum Viable Product) | Design prototype, develop core features, test with early users. | Weeks 9–14 | Pending | Creative Team & Dev Lead
3.2 | Register Business & Legal Structure | Choose entity type, register company name, obtain licenses. | Weeks 10–12 | Pending | Counsel & Admin Team
Phase 4: Launch & Growth
4.1 | Execute Go-to-Market Strategy | Leverage digital marketing, launch landing page, run initial ad campaigns. | Weeks 15–16 | Pending | Marketing & Sales Lead
4.2 | Monitor KPIs & Iterate Strategy | Analyze user engagement, conversion rates, customer feedback. | Ongoing (Post-Launch) | Pending | Product & Analytics Team