## Worksheet
Startup Planning - Planner Template
Version: Startup ¦ Created for Startup Founders & Teams
Phase | Task | Responsible | Deadline | Status
Idea Validation | Conduct market research and customer interviews | Product Manager | 2025-04-15 | Incomplete
Market Research | Analyze competitors and industry trends | Marketing Lead | 2025-04-18 | Pending
Business Model Design | Develop MVP value proposition and revenue model | CEO & Finance Team | 2025-04-20 | Incomplete
Team Formation | Hire key team members (Tech, Marketing, Sales) | HR & CEO | 2025-05-10 | Pending
Funding Strategy | Prepare pitch deck and identify investor targets | CEO & CFO | 2025-04-30 | Incomplete
Product Development | Build MVP and conduct internal testing | Engineering Lead | 2025-06-15 | Pending
Go-to-Market Plan | Create launch strategy and marketing campaign | Marketing Team | 2025-06-10 | Pending
Customer Acquisition | Run pilot program and gather early feedback | Customer Success Lead | 2025-07-01 | Pending
Scaling Strategy | Define KPIs, growth roadmap, and scalability plan | CXO Team | 2025-07-15 | Pending
Additional Notes & Tracking Section
Notes:Regular weekly reviews are recommended. Update status each Friday. Status Legend:Complete (🟢), In Progress (🟡), Incomplete (🔴)