## Worksheet
Startup Planning - Advanced Project Plan
Phase | Task / Deliverable | Owner | Start Date | End Date | Status | % Complete
Phase 1: Ideation & Market Research
Market Opportunity Analysis | Conduct comprehensive market research and competitive analysis | Jane Doe - Product Lead | 2023-10-01 | 2023-10-15 | Completed | 100%
| Identify target customer personas | Jane Doe - Product Lead | 2023-10-01 | 2023-10-07 | Completed | 100%
| Analyze industry trends and pain points | Jane Doe - Product Lead | 2023-10-08 | 2023-10-15 | Completed | 100%
Phase 2: Business Model Development
Business Model Canvas | Create and finalize the business model canvas | Mark Johnson - CEO | 2023-10-16 | 2023-10-31 | Completed | 100%
| Define key partnerships and channels | Mark Johnson - CEO | 2023-10-16 | 2023-10-24 | Completed | 100%
| Establish revenue streams and cost structure | Mark Johnson - CEO | 2023-10-25 | 2023-10-31 | Completed | 100%
Phase 3: MVP Development
MVP Design & Prototyping | Design wireframes and interactive prototype | Sarah Lee - UX/UI Lead | 2023-11-01 | 2023-11-20 | Completed | 100%
| Create high-fidelity mockups for core features | Sarah Lee - UX/UI Lead | 2023-11-01 | 2023-11-10 | Completed | 100%
| Develop clickable prototype for user testing | Sarah Lee - UX/UI Lead | 2023-11-11 | 2023-11-20 | Completed | 100%
Phase 4: Development & Testing
Core Feature Implementation | Develop core application functionality (backend and frontend) | Alex Chen - CTO | 2023-11-21 | 2024-01-31 | Ongoing | 65%
| Build user authentication and profile system | Alex Chen - CTO | 2023-11-21 | 2024-01-15 | Ongoing | 70%
| Implement core feature module A | Alex Chen - CTO | 2023-12-01 | 2024-01-31 | Ongoing | 65%
Phase 5: Launch Preparation
Go-to-Market Strategy | Create detailed launch plan, marketing campaign, and sales strategy | Linda Park - Marketing Director | 2024-01-01 | 2024-03-31 | Delayed | 45%
Phase 6: Launch & Post-Launch
Product Launch | Official product launch and public release | All Team Leads | 2024-04-01 | 2024-04-30 | Delayed | 5%
| Coordinate PR, social media, and influencer outreach | Linda Park - Marketing Director | 2024-03-15 | 2024-04-15 | Delayed | 3%
Total Project Duration: |  |  |  |  | 2023-10-01 to 2024-04-30 (approximately 7 months)