## Worksheet
Startup Planning - Project Plan (Analysis View)
Phase | Task / Milestone | Timeline |  |  | Owner | Status
|  | Start Date | End Date | Duration (Days)
1. Market Analysis & Validation
Phase 1 | Market Research & Competitor Analysis | 2024-03-05 | 2024-03-19 | 15 | Jane Doe (Marketing) | In Progress
Phase 1 | User Persona Development | 2024-03-18 | 2024-03-25 | 8 | Mark Lee (UX Research) | Pending
Key Deliverables: Market Report, Persona Deck, SWOT Analysis
2. Product Development & Design
Phase 2 | Wireframing & UI/UX Prototyping | 2024-03-26 | 2024-04-15 | 21 | Sarah Kim (Design) | Pending
Phase 2 | Figma Prototype Review & Feedback Loop | 2024-04-16 | 2024-04-30 | 15 | Sarah Kim (Design) | Pending
Key Deliverables: Interactive Prototype, Design System Guidelines, Usability Test Plan
3. Technical Development & MVP Build
Phase 3 | Backend API Development (Node.js) | 2024-04-15 | 2024-05-17 | 33 | Tom Chen (Backend) | Pending
Phase 3 | Frontend Development (React.js) | 2024-05-01 | 2024-06-15 | 46 | Lisa Wang (Frontend) | Pending
Key Deliverables: MVP Codebase, API Documentation, CI/CD Pipeline Setup
4. Testing & Validation
Phase 4 | Internal QA & Bug Fixing | 2024-06-16 | 2024-07-15 | 31 | Ryan Patel (QA) | Pending
Key Deliverables: Test Reports, Bug Tracker Status, QA Sign-off Certificate
5. Launch Preparation & Go-to-Market Strategy
Phase 5 | Go-to-Market (GTM) Strategy Finalization | 2024-07-16 | 2024-07-31 | 16 | Jane Doe (Marketing) | Pending
Key Deliverables: GTM Plan, Launch Timeline, Marketing Calendar, Sales Pitch Deck
Overall Project Status
Current Overall Progress |  | 14% | — | — | Predicted Launch Date: | 2024-08-31 (Target)