## Startup Planning - Project Plan
Task ID | Task Name | Start Date | End Date | Assigned To | Status | Priority
T001 | Market Research & Validation | 2025-04-01 | 2025-04-15 | Marketing Team | In Progress | High
T002 | Define Product Features & MVP Scope | 2025-04-16 | 2025-04-30 | Product Team | Pending | High
T003 | Design UI/UX Prototypes | 2025-05-01 | 2025-05-14 | Design Team | Pending | Medium
T004 | Develop MVP Backend Infrastructure | 2025-05-15 | 2025-06-30 | Engineering Team | Pending | High
T005 | Develop MVP Frontend Interface | 2025-05-15 | 2025-06-30 | Engineering Team | Pending | High
T006 | Conduct Internal Testing & QA | 2025-07-01 | 2025-07-14 | QA Team | Pending | Medium
T007 | User Feedback Collection & Iteration | 2025-07-15 | 2025-07-31 | Product Team | Pending | Medium
T008 | Prepare Go-to-Market Strategy & Launch Plan | 2025-08-01 | 2025-08-14 | Marketing Team | Pending | High
T009 | Finalize Legal & Compliance Documentation | 2025-08-15 | 2025-08-31 | Legal Team | Pending | Medium
T010 | Landing Page & Early Sign-Up Campaign Launch | 2025-09-01 | 2025-09-30 | Marketing Team | Pending | High
Note:This project plan is a basic template for startup planning. Adjust dates, responsibilities, and priorities as needed.