## Startup Planning - Project Plan
Startup Planning - Project Plan
Task ID | Task Name | Owner | Start Date | End Date | Status | % Complete
T001 | Market Research & Analysis | Jane Doe | 2025-04-01 | 2025-04-15 | In Progress | 75%
T002 | Define MVP Features | John Smith | 2025-04-16 | 2025-04-30 | Not Started | 0%
T003 | Build Prototype (UI/UX) | Alex Johnson | 2025-05-01 | 2025-05-14 | Not Started | 0%
T004 | Develop Core Product Features | Lisa Wang | 2025-05-15 | 2025-06-30 | Not Started | 0%
T005 | User Testing & Feedback Collection | Daniel Lee | 2025-07-01 | 2025-07-15 | Not Started | 0%
T006 | Finalize Product & Prepare Launch | Sarah Brown | 2025-07-16 | 2025-08-31 | Not Started | 0%
This project plan template is designed for business use in startup planning. Update statuses regularly for accurate tracking.