## Worksheet
Startup Planning - Project Plan (Client View)
Phase | Task | Owner | Due Date | Status | % Complete | Milestones / Notes
Phase 1: Ideation & Market Research
Research | Conduct market gap analysis | Market Analyst | 2025-04-15 | In Progress | 65% | Final report pending client review.
Research | Identify target customer personas | User Researcher | 2025-04-18 | Pending | 0% | To be scheduled after initial findings.
Phase 2: Business Model Development
Strategy | Develop value proposition canvas | Product Strategist | 2025-04-20 | In Progress | 80% | Draft complete; awaiting feedback.
Finance | Create revenue model and pricing strategy | Financial Analyst | 2025-04-25 | Pending | 0% | To begin after value proposition approval.
Phase 3: Product Design & Prototyping
Design | Wireframe core product flow | UX Designer | 2025-04-10 | Completed | 100% | Approved by stakeholders.
Design | Create interactive prototype (Figma) | UI/UX Lead | 2025-04-28 | Pending | 0% | To begin post-wireframe approval.
Phase 4: Planning & Roadmap Finalization
Planning | Finalize product roadmap (Q2–Q4 2025) | Product Manager | 2025-05-03 | Pending | 0% | Depends on prototype review.
Overall Project Status |  | On Track (68% Complete) |  |  | 68% | Next milestone: Prototype review on 2025-04-28