## Worksheet
Task ID | Task Description | Owner | Status | Start Date | End Date | Budget (USD)
T001 | Market Research & Validation | Product Team | To Do | 2024-04-01 | 2024-04-15 | $3,500
T002 | Define MVP Features | Product Manager | In Progress | 2024-04-16 | 2024-05-01 | $5,000
T003 | Design UI/UX Prototype | UI/UX Designer | In Progress | 2024-05-02 | 2024-05-15 | $6,800
T004 | Develop Core Platform (MVP) | Dev Team Lead | To Do | 2024-05-16 | 2024-07-15 | $35,000
T005 | Alpha Testing (Internal) | QA Team | To Do | 2024-07-16 | 2024-08-15 | $8,500
T006 | User Feedback & Iteration | Product Manager | To Do | 2024-08-16 | 2024-09-30 | $12,000
T007 | Finalize Product & Launch Plan | CEO & Marketing Lead | To Do | 2024-10-01 | 2024-10-31 | $7,500
T008 | Go-to-Market Launch (Public) | Marketing Team | To Do | 2024-11-01 | 2024-11-30 | $45,000