## Worksheet
Startup Planning - Project Plan Dashboard
Track milestones, tasks, and progress for your new venture
Task ID | Task Name | Owner | Deadline | Status | Prioritization | Budget (USD)(Est.)
TP-001 | Market Research & Feasibility Study | Jane Doe | 2024-03-15 | In Progress | High | $5,000✓ $3,200 spent
TP-002 | Business Model Validation | Mark Lee | 2024-03-25 | In Progress | High | $8,000✓ $1,500 spent
TP-003 | Prototype Development (MVP) | Alice Chen | 2024-04-15 | Pending | High | $35,000✓ $8,900 spent
TP-004 | User Testing & Feedback Collection | Tom Wilson | 2024-05-15 | Pending | Medium | $6,500✓ $1,200 spent
TP-005 | Legal Structure & Incorporation | Sarah Kim | 2024-03-31 | Completed | High | $4,800✓ $4,750 spent
TP-006 | Funding Proposal & Investor Pitch Deck | Daniel Green | 2024-04-30 | In Progress | High | $7,500✓ $3,100 spent
TP-007 | Website Development (Landing Page) | Lisa Brown | 2024-04-15 | In Progress | Medium | $9,000✓ $6,300 spent
TP-008 | Initial Marketing Campaign Setup | James Taylor | 2024-05-15 | Pending | Medium | $12,000✓ $2,400 spent
Total Budget Used: | [5 empty] | $32,450Total Estimated: $97,800
Overall Progress:65%