## Worksheet
Startup Planning - Project Plan (Extended)
Phase | Task | Owner | Start Date | End Date | Duration (Days) |  | Dependencies |  | Status
Phase 1: Ideation | Market Research & Opportunity Analysis | CEO / CMO | 2025-04-01 | 2025-04-15 | 15 days |  | None (Start) |  | In Progress
| Competitor Analysis & SWOT Review | Product Manager / Analyst | 2025-04-16 | 2025-04-30 | 15 days |  | Market Research Complete |  | In Progress
| Core Value Proposition Definition | CEO / CMO / UX Lead | 2025-05-01 | 2025-05-10 | 10 days |  | Competitor Analysis Complete |  | In Progress
| Finalize MVP Concept & Vision Doc | CEO / Leadership Team | 2025-05-11 | 2025-05-15 | 5 days |  | Value Prop Definition Complete |  | Completed
Phase 2: Planning | Build Project Roadmap (Q2–Q4) | Project Manager / PMO | 2025-05-16 | 2025-05-31 | 16 days |  | MVP Concept Approved |  | In Progress
| Resource & Budget Allocation Plan | Finance Lead / CFO | 2025-06-01 | 2025-06-15 | 15 days |  | Roadmap Draft Complete |  | In Progress
| Team Structure & Hiring Plan | HR Director / CEO | 2025-06-16 | 2025-06-30 | 15 days |  | Budget Plan Approved |  | In Progress
| Approval: Full Startup Plan Document (v1.0) | CEO / Board Advisor | 2025-07-01 | 2025-07-05 | 5 days |  | Hiring & Budget Plans Complete |  | Delayed (Pending Review)
Phase 3: Development Prep | Technical Architecture Design | CTO / Lead Architect | 2025-07-06 | 2025-07-31 | 26 days |  | Plan Document Approved |  | In Progress
| Design MVP UI/UX Wireframes & Prototypes | UI/UX Designer / Product Manager | 2025-08-01 | 2025-08-31 | 31 days |  | Architecture Design Approved |  | In Progress
| Finalize Tech Stack & Third-Party Integrations | CTO / DevOps Lead | 2025-09-01 | 2025-09-15 | 15 days |  | Wireframes Approved |  | In Progress
| Development Readiness Sign-Off (v1) | CTO / Project Manager | 2025-09-16 | 2025-09-30 | 15 days |  | Tech Stack Finalized |  | In Progress
Phase 4: Execution & Launch | Begin MVP Development (Sprint 1-6) | Development Team / Scrum Master | 2025-10-01 | 2025-11-30 | 61 days |  | Ready Sign-off Complete |  | In Progress
| Marketing & Pre-Launch Campaigns Setup | Marketing Lead / CMO | 2025-10-15 | 2025-11-30 | 46 days |  | Sprint 3 Completed (MVP MVP) |  | In Progress
| Soft Launch to Beta Users (V1.0) | Product Manager / Support | 2025-12-01 | 2025-12-31 | 30 days |  | MVP Dev Complete, Marketing Active |  | Delayed (Waiting on QA)
| Official Product Launch (V1.0) | CEO / CMO / Team | 2026-01-05 | 2026-01-15 | 11 days |  | Beta Feedback Collected, Final Fixes Done |  | Delayed (Pending)
Total Project Duration: | [5 empty] | 370 days |  | Critical Path Milestones |  | In Progress (On Track)
Overall Project Progress:47% Complete
This project plan was generated on April 5, 2025. Last updated by Project Manager. Status reflects real-time data from the startup dashboard.