## Worksheet
Startup Planning - Project Plan - Financial View
Phase / Milestone | Timeline (Months) | Cost Estimate ($) | Funding Source | Budget Allocated ($) | Actual Spend ($) | % of Budget Used
Total Project Budget Summary | [5 empty] | $0.00
Phase 1: Concept Development & Market Research
Market Research & Analysis | 0-2 | 15,000 | Seed Investment | 15,000 | - | -
Phase 2: Product Development & Prototyping
UI/UX Design | 1-4 | 25,000 | Seed Investment / Grants | 25,000 | -
Software Development (MVP) | 3-7 | 120,000 | VC Funding (Round A) | 120,000 | -
Phase 3: Launch Preparation & Go-to-Market Strategy
Marketing Campaign Planning | 5-8 | 18,000 | Budget Reserve | 18,000 | -
Phase 4: Product Launch & Early Growth
Launch Event & PR Blitz | 8-9 | 30,000 | Revenue Reinvestment (Seed) | 30,000 | -
Phase 5: Scale & Operational Expansion
Team Hiring (Dev, Sales, Support) | 9-12 | 80,000 | Series A Funding | 80,000 | -
Total Project Cost Estimate | [5 empty] | $318,000
Note: All values are estimates. Actual costs may vary based on market conditions and operational needs.