## Worksheet
Startup Planning - Freelancer Project Plan
Task ID | Task Description | Assigned To | Start Date | End Date | Status | % Complete
TASK-001 | Market Research & Competitor Analysis | Jane Doe, Market Analyst | 2025-04-01 | 2025-04-15 | In Progress | 65%
TASK-002 | Business Model Development | John Smith, Business Strategist | 2025-04-03 | 2025-04-18 | In Progress | 78%
TASK-003 | Prototype Design (UI/UX) | Alice Brown, UI/UX Designer | 2025-04-05 | 2025-04-25 | In Progress | 47%
TASK-004 | Technical Architecture Planning | Mike Johnson, CTO | 2025-04-10 | 2025-04-30 | In Progress | 68%
TASK-005 | Funding Pitch Deck Creation | Sarah Lee, Marketing Lead | 2025-04-12 | 2025-04-30 | In Progress | 81%
TASK-006 | Legal Structure & IP Registration | David Kim, Legal Consultant | 2025-04-15 | 2025-04-30 | Completed | 100%
TASK-007 | Team Onboarding & Roles Assignment | Lisa Wang, HR Manager | 2025-04-18 | 2025-04-30 | In Progress | 60%
TASK-008 | Initial MVP Development (Frontend) | Tom Clark, Frontend Developer | 2025-04-20 | 2025-05-15 | In Progress | 38%
TASK-009 | Initial MVP Development (Backend) | Lisa Patel, Backend Developer | 2025-04-21 | 2025-05-18 | In Progress | 35%
TASK-010 | Project Kickoff & Planning Meeting | All Team Members | 2025-04-01 | 2025-04-15 | Completed | 100%