## Worksheet
Startup Planning - Project Plan Template
Phase / Task | Owner | Start Date | End Date | Status | Progress (%)
Phase 1: Idea Validation | - | 2024-04-05 | 2024-04-15 | Pending | 0%
Conduct market research | Jane Smith | 2024-04-05 | 2024-04-10 | Pending | 15%
Identify customer pain points | Jane Smith | 2024-04-07 | 2024-04-13 | Pending | 5%
Phase 2: Business Model Design | - | 2024-04-16 | 2024-05-01 | Pending | 0%
Create business model canvas | Mike Johnson | 2024-04-16 | 2024-04-19 | Pending | 8%
Determine pricing strategy | Mike Johnson | 2024-04-18 | 2024-04-23 | Pending | 15%
Phase 3: MVP Development | - | 2024-05-02 | 2024-06-15 | Pending | 0%
Design wireframes and prototypes | Alex Brown | 2024-05-02 | 2024-05-15 | Pending | 18%
Develop core product features | Alex Brown | 2024-05-16 | 2024-06-15 | Pending | 3%
Phase 4: Testing & Feedback | - | 2024-06-16 | 2024-07-15 | Pending | 0%
Recruit beta testers | Lisa Chen | 2024-06-16 | 2024-06-30 | Pending | 5%
Collect and analyze feedback | Lisa Chen | 2024-07-01 | 2024-07-15 | Pending | 3%
Phase 5: Launch Preparation | - | 2024-07-16 | 2024-08-15 | Pending | 0%
Create marketing materials | Tamara Lee | 2024-07-16 | 2024-08-05 | Pending | 13%
Finalize launch timeline | Tamara Lee | 2024-08-06 | 2024-08-15 | Pending | 3%
Phase 6: Official Launch | - | 2024-08-16 | 2024-08-31 | Pending | 0%
Go live with MVP | All Team Members | 2024-08-16 | 2024-08-31 | Pending | 0%
Total Duration | 2024-04-05 to 2024-08-31