## Worksheet
Startup Planning - Project Plan
Large Business Style ¦ Version 2.0 ¦ Updated: April 2025
Phase | Task Name | Description | Owner(s) | Start Date | End Date | Status | Completed (%)
Phase 1: Strategy & Vision
Strategy | Define Core Business Model | Develop the foundational business model including value proposition, customer segments, and revenue streams. | Alice Chen (CEO) | 2025-04-01 | 2025-04-15 | In Progress | 65%
Strategy | Create Vision & Mission Statement | Craft a compelling vision and mission that aligns with long-term goals. | Brian Reed (CTO) | 2025-04-10 | 2025-04-18 | In Progress | 70%
Phase 2: Market Research & Validation
Research | Conduct Competitor Analysis | Analyze key competitors, market positioning, and gaps in the industry. | Catherine Lopez (Market Lead) | 2025-04-15 | 2025-04-30 | In Progress | 80%
Research | Customer Discovery Interviews (n=25) | Conduct in-depth interviews to validate pain points and needs. | Daniel Kim (UX Researcher) | 2025-04-18 | 2025-05-10 | In Progress | 68%
Phase 3: Product Development (MVP)
Development | Design MVP Wireframes | Create high-fidelity wireframes based on user feedback. | Eva Turner (Lead Designer) | 2025-05-01 | 2025-05-14 | Completed | 100%
Development | Develop MVP Backend (API) | Build core backend infrastructure and APIs. | Felix Wong (Backend Engineer) | 2025-05-10 | 2025-06-15 | In Progress | 45%
Phase 4: Go-to-Market Strategy
GTM | Build Launch Marketing Campaign | Develop digital advertising, email sequences, and social media strategy. | Gina Patel (Marketing Director) | 2025-06-01 | 2025-06-30 | Delayed | 35%
Phase 5: Operations & Team Building
Operations | Recruit Key Leadership Roles (CFO, CMO) | Hire senior executives for finance and marketing. | Hannah Taylor (HR Director) | 2025-06-10 | 2025-07-15 | In Progress | 75%
Total Project Progress: | [5 empty] | Overall Completion Rate: 64%