## Worksheet
Startup Planning - Monthly Project Plan
Task ID | Task Name | Owner | Start Date | End Date | Status | Budget (USD)
PRJ-001 | Market Research & Validation | Jane Smith | 2025-04-01 | 2025-04-15 | Completed | $3,500
PRJ-002 | Business Model Development | Mark Lee | 2025-04-16 | 2025-04-30 | Completed | $5,000
PRJ-011 | User Persona Creation | Sarah Johnson | 2025-05-01 | 2025-05-14 | In Progress | $4,800
PRJ-012 | Wireframe & UI Design | Dave Chen | 2025-05-15 | 2025-05-31 | In Progress | $7,600
PRJ-021 | Core Feature Development (Phase 1) | Lisa Patel | 2025-06-01 | 2025-06-30 | Delayed | $48,900
PRJ-031 | Alpha Testing & Bug Fixing | Tony Rivera | 2025-07-01 | 2025-07-15 | Delayed | $9,400
PRJ-041 | Go-to-Market Strategy & Campaigns | Maria Gomez | 2025-07-16 | 2025-07-31 | Not Started | $36,800
Total Budget (5 Months): | [5 empty] | $126,000