## Worksheet
Startup Planning - Project Plan (Multi-Page)
Project Name:[Insert Startup Name]
Date:[Insert Date]
Phase | Task | Timeline |  |  | Owner
|  | Start Date | End Date | DURATION (Days)
Phase 1: Concept Development | Market Research & Validation | 2025-04-01 | 2025-04-15 | 15 | Jane Doe - Product Lead
| Define Core Value Proposition | 2025-04-16 | 2025-04-30 | 15 | Jane Doe - Product Lead
| Build Initial Business Model Canvas | 2025-05-01 | 2025-05-10 | 10 | Jane Doe - Product Lead
| Internal Pitch Deck Finalization | 2025-05-11 | 2025-05-15 | 5 | Jane Doe - Product Lead
Phase 2: Planning & Strategy | Develop Go-to-Market Strategy | 2025-05-16 | 2025-06-15 | 30 | Alex Rivera - Marketing Lead
| Create Financial Projections (3 Years) | 2025-05-16 | 2025-06-14 | 30 | Maria Chen - Finance Lead
| Legal Structure & IP Protection Planning | 2025-06-16 | 2025-07-31 | 45 | Sam Wilson - Legal Advisor
| Risk Assessment & Mitigation Plan | 2025-06-16 | 2025-07-31 | 45 | Diana Liu - Operations Lead
Phase 3: Team & Funding | Recruit Core Founding Team | 2025-08-01 | 2025-08-31 | 31 | Peter Kim - HR & Culture Lead
| Fundraising Strategy Development | 2025-08-01 | 2025-09-14 | 45 | Maria Chen - Finance Lead
| First Round Pitch & Investor Outreach | 2025-09-15 | 2025-11-30 | 77 | Alex Rivera - Marketing Lead
| Funding Close & Capital Allocation Plan | 2025-12-01 | 2025-12-31 | 31 | Maria Chen - Finance Lead
Phase 4: MVP Development | Define MVP Scope & Features | 2026-01-01 | 2026-01-31 | 31 | Jane Doe - Product Lead
| Build MVP (Frontend & Backend) | 2026-02-01 | 2026-05-31 | 120 | Liam O'Connor - CTO
| MVP Testing & Feedback Collection (Internal/Alpha) | 2026-06-01 | 2026-07-31 | 61 | Jane Doe - Product Lead
| MVP Refinement Based on Feedback | 2026-08-01 | 2026-08-31 | 31 | Liam O'Connor - CTO
Phase 5: Launch & Growth | Finalize Go-to-Market Plan (Beta) | 2026-09-01 | 2026-11-30 | 91 | Alex Rivera - Marketing Lead
| Beta Launch & User Onboarding Campaigns | 2026-12-01 | 2027-03-31 | 121 | Alex Rivera - Marketing Lead
| Collect Feedback & Iterate (Product) | 2026-12-01 | 2027-03-31 | 121 | Jane Doe - Product Lead
| Scale Operations & Team Expansion (Hiring) | 2027-04-01 | 2027-12-31 | 305 | Peter Kim - HR & Culture Lead
Project Milestones & Key Performance Indicators (KPIs)
Milestone | Due Date | Status | Target KPI | Actual KPI | Notes/Comments
MVP Feature Complete (Core Functionality) | 2026-05-31 | In Progress | 95% Feature Completeness | - | On track with minor UI delays.
First 100 Beta Users Acquired | 2026-12-31 | To Be Started | Reach: 100 users (via referral & social) | - | Marketing campaign aligned with user persona.
Product-Market Fit Validation (Survey + Engagement Rate) | 2027-06-30 | To Be Started | Engagement: 40% weekly active users | - | KPIs to be tracked post-beta launch.
First Revenue Milestone: $10K MRR | 2027-12-31 | To Be Started | MRR: $10,000/month by end of year | - | Based on 5% conversion from free to paid.
Funding Round Closed: $1.2M Seed Round | 2025-11-30 | Completed | $1,200,000 raised from 8 investors | $1,250,000 (actual) | Funds exceeded target by 4.2%.
Team Size: 15 Full-Time Employees | 2027-03-31 | To Be Started | Hire 15 key roles across Product, Engineering, Marketing & Ops | - | HR hiring pipeline in progress.
Project Summary & Gantt Chart Overview
Total Project Duration | 24 Months (Starting 2025-04-01)
Key Phases & Duration | Phase 1: 30 Days Phase 2: 75 Days Phase 3: 147 Days Phase 4: 243 Days Phase 5: ~600 Days (Ongoing)
Next Major Milestone | Beta Launch – December 1, 2026
Resource Allocation & Budget Forecast
Category | Team Member (Role) | Hours/Week | Type | Budget (USD) | Status | Start Date | End Date
Engineering & Product | Liam O'Connor - CTO (1 FTE) | 40 | Full-Time | $250,000 | Active (26/12) | 2025-08-15 | 2034-12-31
Engineering & Product | Jane Doe - Lead Product (1 FTE) | 40 | Full-Time | $220,000 | In Progress (3/5) | 2025-08-15 | 2034-12-31
Marketing & Growth | Alex Rivera - Marketing Lead (1 FTE) | 40 | Full-Time | $200,000 | In Progress (2/3) | 2025-11-31 | 2034-12-31
Operations & Finance | Maria Chen - Finance Lead (0.5 FTE) | 20 | Part-Time | $75,000 | In Progress (1/3)
Legal & HR | Sam Wilson - Legal Advisor (Contract) | 10 | Contract | $35,000 | In Progress (2/4)
Total Projected Budget: |  |  |  | $780,000 | — | —
Note: All dates and budgets are subject to change based on project progress, funding outcomes, and market conditions.