## Startup Planning - Project Plan
Startup Planning - Project Plan (Office Use)
Task ID | Task Name | Owner | Start Date | End Date | Status | % Complete | Critical Path?
Project Overview & Objectives
001 | Define Startup Vision & Mission | CEO | 2024-04-01 | 2024-04-15 | Pending | 0% | No
002 | Create Business Model Canvas | Product Lead | 2024-04-16 | 2024-04-30 | In Progress | 65% | No
003 | Develop Go-to-Market Strategy | Marketing Head | 2024-05-01 | 2024-05-15 | Pending | 0% | No
M1 | Finalize Business Plan (Draft) | CEO / CFO | 2024-05-16 | 2024-05-31 | Pending | 0% | No
Team Structure & Responsibilities
004 | Recruit Core Team Members | Hiring Manager | 2024-06-01 | 2024-06-30 | Pending | 5% | No
005 | Assign Roles & Responsibilities Matrix (RACI) | Project Manager | 2024-07-01 | 2024-07-15 | Pending | 0% | No
Product Development Phase
006 | Conduct Market Research & Validation | Product Manager | 2024-05-31 | 2024-06-30 | In Progress | 85% | No
007 | Design MVP Wireframes & Prototypes | UX Designer | 2024-07-01 | 2024-07-31 | Pending | 5% | No
CP1 | Develop Minimum Viable Product (MVP) | CTO / Dev Team | 2024-08-01 | 2024-10-31 | Pending | 5% | Yes
M2 | Complete MVP Development (Internal Review) | CPO / Engineering Lead | 2024-11-01 | 2024-11-30 | Pending | 0% | No
Funding & Financial Strategy
008 | Prepare Pitch Deck for Investors | CEO / CFO | 2024-06-15 | 2024-07-31 | In Progress | 75% | No
009 | Identify & Engage Potential Investors | CFO / Investor Relations Lead | 2024-07-15 | 2024-11-30 | Pending | 5% | No
CP2 | Raise Seed Funding Round ($1.5M) | CFO / CEO | 2024-12-01 | 2025-03-31 | Pending | 5% | Yes
Go-to-Market & Operations Launch
010 | Finalize Customer Onboarding Flow | Product Manager / Ops Lead | 2025-03-01 | 2025-04-30 | Pending | 1% | No
CP3 | Launch Beta Version to Early Adopters | CPO / Marketing Head | 2025-05-01 | 2025-06-30 | Pending | 3% | Yes
M3 | Official Public Launch (v1.0) | CEO / CTO | 2025-07-01 | 2025-07-31 | Pending | 3% | No
Project Summary & Key Metrics
Total Tasks: | 16 | Completed: | 2 | In Progress: | 8 (50%)
Last Updated: April 5, 2024 ¦ Prepared for Internal Office Use Only