## Worksheet
Startup Planning - One Page Project Plan
Template Type: Project Plan ¦ Purpose: Startup Planning ¦ Version: One Page
Phase / Milestone | Key Activities | Responsible Party | Start Date | End Date | Status
Phase 1: Ideation & Market Validation
Market Research | Conduct competitive analysis, identify target audience, define problem statement. | Founder / Product Manager | 2023-10-01 | 2023-10-15 | In Progress
Idea Refinement & Concept Development | Develop MVP concept, sketch user flows, finalize value proposition. | Product Team / UX Designer | 2023-10-16 | 2023-10-31 | Pending
Phase 2: Business Model & Planning
Business Model Canvas | Complete all sections of the business model canvas (customer segments, channels, revenue streams, etc.). | Founder / CFO | 2023-11-01 | 2023-11-10 | Pending
Financial Projections (Year 1–3) | Build revenue, cost, and cash flow models; include break-even analysis. | CFO / Finance Consultant | 2023-11-11 | 2023-11-25 | Pending
Phase 3: Product Development & MVP Launch
UI/UX Design (Wireframes & Prototypes) | Create wireframes, interactive prototypes, and conduct usability testing. | UX Designer / Product Manager | 2023-11-26 | 2023-12-15 | Pending
MVP Development (Frontend & Backend) | Develop core features, implement API integrations, perform unit testing. | Engineering Team | 2023-12-16 | 2024-01-31 | Pending
Phase 4: Launch & Early Adoption
Pre-Launch Marketing Campaign | Build landing page, run social media ads, collect early user sign-ups. | Marketing Lead / Growth Hacker | 2024-01-01 | 2024-02-15 | Pending
MVP Launch & Beta Testing | Release MVP to early users, gather feedback, fix critical bugs. | Product Manager / Engineering Team | 2024-02-16 | 2024-03-15 | Pending
Phase 5: Fundraising & Scaling Strategy
Fundraising Preparation (Pitch Deck, Financials) | Create investor pitch deck, update financials, prepare due diligence documents. | Founder / CFO | 2024-03-16 | 2024-04-15 | Pending
Fundraising & Investor Outreach | Pitch to angel investors, venture capital firms; finalize term sheet. | Founder / CEO | 2024-04-16 | 2024-05-31 | Pending
Total Timeline: |  |  |  |  | 2023-10-01 to 2024-05-31