## Startup Planning - Project Plan
Startup Planning - Project Plan
Template Type:Project Plan ¦Style/Version:Personal Use
# | Task | Start Date | End Date | Responsible | Status
1 | Define Business Idea and Vision | 2025-04-01 | 2025-04-07 | Founder | Pending
2 | Market Research & Analysis | 2025-04-08 | 2025-04-14 | Marketing Lead | In Progress
3 | Create Business Model Canvas | 2025-04-15 | 2025-04-18 | Founder / Product Lead | Pending
4 | Develop MVP (Minimum Viable Product) | 2025-04-19 | 2025-05-16 | Development Team | Pending
5 | User Testing & Feedback Collection | 2025-05-17 | 2025-06-14 | Product Manager / UX Designer | Pending
6 | Finalize Product and Prepare Launch | 2025-06-15 | 2025-07-13 | All Team Members | Pending
7 | Marketing Campaign & Launch Strategy | 2025-06-01 | 2025-07-31 | Marketing Team | Pending
8 | Secure Initial Funding (Seed Round) | 2025-04-01 | 2025-07-31 | Founder / CFO | Pending