## Worksheet
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Owner | % Complete(Progress)
Phase 1: Ideation & Market Research
TASK-001 | Define core business idea | 2025-04-01 | 2025-04-15 | 15 | In Progress | Alice Johnson | 75%
TASK-002 | Conduct competitor analysis | 2025-04-16 | 2025-04-30 | 15 | To Do | Brian Smith | 10%
Milestone: Finalize business concept (Approved)
Phase 2: Team Formation & Organizational Setup
TASK-003 | Recruit core founding team | 2025-05-01 | 2025-05-14 | 14 | To Do | Claire Brown | 0%
Milestone: Core team onboarded (Target: 2025-05-14)
Phase 3: Product Development & MVP
TASK-004 | Design UI/UX prototype | 2025-05-15 | 2025-06-15 | 31 | To Do | Daniel Lee | 0%
Milestone: MVP prototype ready (Target: 2025-06-15)
Phase 4: Legal Setup & Fundraising
TASK-005 | Register business entity and IP | 2025-06-16 | 2025-07-14 | 30 | To Do | Elena Martinez | 0%
Milestone: Legal and IP secured (Target: 2025-07-14)
Phase 5: Pre-Launch Marketing & Go-To-Market
TASK-006 | Develop go-to-market strategy | 2025-07-15 | 2025-08-14 | 31 | To Do | Fred Wilson | 0%
Milestone: Launch readiness (Target: 2025-08-14)
Overall Project Status: | [6 empty] | 18%