## Startup Planning - Project Plan
Startup Planning - Project Plan
Printable Version ¦ Template Type: Project Plan ¦ Purpose: Startup Planning
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | Priority
T001 | Define Business Model | CEO & Team | 2025-04-01 | 2025-04-15 | In Progress | Highest
T002 | Conduct Market Research | Marketing Lead | 2025-04-16 | 2025-04-30 | To Do | High
T003 | Develop MVP Prototype | Product Team | 2025-05-01 | 2025-06-15 | To Do | Highest
T004 | Secure Seed Funding | CEO & CFO | 2025-05-15 | 2025-07-31 | To Do | High
T005 | Build Core Development Team | Hiring Manager | 2025-04-18 | 2025-06-10 | In Progress | High
T006 | Create Brand Identity & Website | Design & Marketing Team | 2025-06-16 | 2025-07-31 | To Do | Medium
T007 | Launch Beta Testing Program | Product & QA Team | 2025-08-01 | 2025-09-30 | To Do | High