## Worksheet
Startup Planning - Quarterly Project Plan
Quarter | Phase | Key Objectives | Milestones | Responsible Team/Person | Status
Q1 2024 | Market Research & Validation | Define target audience, validate problem-solution fit, conduct competitor analysis. | Finalize customer personas; Complete market survey (500+ responses). | Product Team & Market Analysts | Pending
| Initial Prototyping | Build MVP concept, develop wireframes, gather feedback. | Create 3 interactive prototypes; Present to 10 early users. | UX/UI Designers & Product Manager | In Progress
| Funding Strategy | Develop pitch deck, identify investors, prepare financial model. | Secure $250K in pre-seed funding. | CEO & Finance Lead | Pending
Q2 2024 | MVP Development | Build core product features based on validated feedback. | Complete first working version of MVP (v0.1). | Engineering Team | In Progress
| User Testing & Feedback Loop | Run beta test with 50 early adopters; iterate based on feedback. | Collect and analyze user behavior data; deliver v0.2 update. | Product Manager & QA Team | Pending
| Growth Marketing Initiation | Create landing page, start social media channels, run first ad campaign. | Generate 1,000 website visits; collect 200 email signups. | Marketing Team | Pending
Q3 2024 | Product Refinement & Scaling Prep | Improve performance, security, and scalability; finalize architecture. | Pass all QA stress tests; prepare deployment pipeline. | Engineering & DevOps Team | Pending
| Customer Acquisition | Leverage marketing channels to acquire first 1,000 active users. | Reach 1,000 monthly active users (MAU). | Marketing & Sales Team | Pending
| Funding Round (Seed) | Present growth metrics to investors; close seed funding round. | Raise $1.5M in seed funding. | CEO & CFO | Pending
Q4 2024 | Full Product Launch | Officially release product to public; activate customer onboarding. | Launch on app stores and web platform with full feature set. | All Teams | Pending
| Customer Retention & Engagement | Implement feedback system, user education materials, and retention campaigns. | Achieve 70% 30-day user retention rate. | CX & Product Team | Pending
| Plan for Next Year | Review performance, set Q1 2025 goals, allocate budget. | Finalize annual roadmap and KPIs. | Executive Team | Pending