## Worksheet
Startup Planning - Project Plan Report Version
Company:Innovatech Solutions Inc.
Prepared For:Executive Board
Project Name:NextGen Platform Launch
Date Prepared:June 15, 2024
Phase | Task Name | Start Date | End Date | Status | Owner(s)
1. Discovery & Planning | Market Research & Competitor Analysis | 2024-06-15 | 2024-06-30 | In Progress | Jane Doe (Product Manager)
| Define Target User Persona | 2024-06-18 | 2024-07-05 | In Progress | Mike Chen (UX Researcher)
| Finalize Business Model Canvas | 2024-06-25 | 2024-07-10 | Pending | Alex Taylor (CEO)
2. Design & Prototyping | User Interface Wireframing | 2024-07-11 | 2024-07-31 | Pending | Sarah Kim (UI Designer)
| Interactive Prototype Development | 2024-08-01 | 2024-08-15 | Pending | David Lee (Frontend Dev)
| User Testing & Feedback Collection | 2024-08-16 | 2024-08-31 | Pending | Jane Doe (Product Manager)
3. Development & Testing | Backend API Development - Phase 1 | 2024-09-01 | 2024-09-30 | Pending | Alex Taylor (CTO)
| Frontend Implementation - Core Modules | 2024-10-01 | 2024-10-31 | Pending | David Lee (Frontend Dev)
| Integration Testing & Bug Fixes | 2024-11-01 | 2024-11-30 | Pending | Lisa Wu (QA Lead)
| Performance & Security Audits | 2024-12-01 | 2024-12-15 | Pending | Ryan Patel (DevOps)
4. Launch & Post-Launch | Final Deployment to Production | 2024-12-16 | 2024-12-31 | Pending | Ryan Patel (DevOps)
| Marketing Campaign Execution | 2025-01-01 | 2025-01-31 | Pending | Maria Garcia (Marketing Lead)
| Post-Launch Monitoring & Iteration | 2025-02-01 | 2025-06-30 | Pending | All Teams
Total Duration: |  |  |  | 12 months (June 2024 - May 2025)
Note:This project plan is a living document and subject to updates as new information becomes available. Status reflects the current state as of June 15, 2024.