## Startup Planning - Project Plan
Startup Planning - Project Plan
Task ID | Task Name | Start Date | End Date | Status | Responsible Person
T001 | Market Research | 2023-10-01 | 2023-10-15 | In Progress | Jane Doe
T002 | Business Model Development | 2023-10-16 | 2023-10-31 | Not Started | John Smith
T003 | Product Prototype Design | 2023-11-01 | 2023-11-20 | Not Started | Alice Johnson
T004 | Funding Pitch Preparation | 2023-11-21 | 2023-12-05 | Not Started | Bob Wilson
T005 | Team Recruitment & Hiring | 2023-12-06 | 2024-01-15 | Not Started | Sarah Brown
T006 | Legal & Regulatory Setup | 2024-01-16 | 2024-01-31 | Not Started | Mike Davis
T007 | Final Product Development | 2024-02-01 | 2024-03-15 | Not Started | Alice Johnson
T008 | Go-to-Market Strategy | 2024-03-16 | 2024-04-15 | Not Started | Jane Doe
T009 | Launch & Initial Marketing Campaign | 2024-04-16 | 2024-05-31 | Not Started | Bob Wilson