## Startup Planning - Project Plan
Startup Planning - Project Plan (Small Business)
Task ID | Task Description | Assigned To | Start Date | End Date | Status
T001 | Define Business Concept and Mission Statement | Founder/CEO | 2024-04-05 | 2024-04-12 | Pending
T002 | Conduct Market Research and Competitor Analysis | Marketing Lead | 2024-04-13 | 2024-04-26 | In Progress
T003 | Develop Business Model Canvas | Product Manager | 2024-04-15 | 2024-04-28 | In Progress
T004 | Create Financial Projections (3-Year) | Finance Manager | 2024-04-18 | 2024-05-15 | Pending
T005 | Register Business and Obtain Licenses/Permits | Legal Officer | 2024-04-29 | 2024-05-18 | Pending
T006 | Build MVP (Minimum Viable Product) | Development Team | 2024-05-15 | 2024-07-31 | Pending
T007 | Design Brand Identity (Logo, Colors, Fonts) | Design Lead | 2024-05-16 | 2024-06-15 | Pending
T008 | Set Up Company Website & Landing Page | Web Developer | 2024-06-15 | 2024-07-15 | Pending
T009 | Prepare Pitch Deck for Investors | CEO & Marketing Lead | 2024-07-16 | 2024-08-15 | Pending
T010 | Launch Pilot Program with Beta Users | Product Manager & QA Lead | 2024-08-16 | 2024-10-31 | Pending
Total Tasks: |  |  |  |  | 10