## Startup Planning - Project Plan
Startup Planning - Project Plan (Startup Style)
Task ID | Task Name | Description | Owner | Start Date | End Date | Status
#SP-001 | Market Research & Validation | Analyze target market, customer needs, and competitive landscape. | Product Manager | 2025-04-01 | 2025-04-15 | In Progress
#SP-002 | Business Model Design | Define revenue streams, pricing strategy, and value proposition. | CEO & CFO | 2025-04-16 | 2025-04-30 | Pending
#SP-003 | Prototype Development (MVP) | Create initial product prototype for testing. | Lead Developer | 2025-05-01 | 2025-06-15 | Pending
#SP-004 | User Testing & Feedback Loop | Conduct usability tests with real users and collect feedback. | UX Designer & Product Manager | 2025-06-16 | 2025-07-15 | Pending
#SP-005 | Funding Strategy & Pitch Deck | Develop pitch materials and identify investor targets. | CEO & Investor Relations Lead | 2025-07-16 | 2025-08-31 | Pending
#SP-006 | Team Hiring & Org Setup | Recruit core team members and define roles. | HR Manager & CEO | 2025-08-15 | 2025-10-31 | Pending
#SP-007 | Launch Preparation (Go-to-Market) | Finalize marketing campaigns, sales channels, and launch timeline. | Marketing & Sales Lead | 2025-11-01 | 2025-11-30 | Pending
#SP-008 | Soft Launch & Iteration | Release to early adopters and refine based on feedback. | Product Team | 2025-12-01 | 2025-12-31 | Pending