## Worksheet
Startup Planning - Project Plan (Summary View)
Project Name:InnovateX Startup Launch
Start Date:2025-04-01
End Date:2026-03-31
Status:In Progress
Phase | Key Milestones | Owner | Status | Due Date | Budget (USD)
Phase 1: Ideation & Market Research | • Define core product concept • Conduct target market analysis • Perform competitor benchmarking • Validate problem-solution fit | Product Team | Completed | 2025-04-15 | $15,000
Phase 2: Business Model Development | • Finalize value proposition • Build revenue model • Develop go-to-market strategy • Draft business plan | Business Team | In Progress | 2025-06-30 | $25,000
Phase 3: MVP Development | • Design UI/UX prototypes • Develop core product features • Perform internal testing • Gather user feedback | Engineering Team | Pending | 2025-10-15 | $85,000
Phase 4: Funding & Investor Pitch | • Prepare pitch deck • Identify investor targets • Conduct pilot investor meetings • Secure seed funding | Finance & Founders | Pending | 2025-12-31 | $10,000
Phase 5: Beta Launch | • Onboard beta users • Monitor performance metrics • Fix critical bugs • Collect user feedback | Product & QA Team | Pending | 2026-01-31 | $35,000
Phase 6: Full Launch | • Deploy to production • Initiate marketing campaign • Monitor user acquisition • Scale infrastructure | Marketing & Ops Team | Pending | 2026-03-15 | $65,000
Total: | Grand Total Budget: |  |  |  | $235,000