## Worksheet
Startup Planning - Project Plan Template (Team Use)
Task ID | Task Description | Owner | Due Date | Status | Progress (%)
TP-001 | Define startup vision and mission statement | CEO & Founding Team | 2023-10-15 | In Progress | 60
TP-002 | Conduct market research and competitor analysis | Marketing Lead | 2023-11-01 | Planned | 0
TP-003 | Develop business model canvas | Product Manager & CEO | 2023-10-25 | In Progress | 75
TP-004 | Finalize product roadmap (Q1–Q4) | Product Manager | 2023-11-15 | Planned | 0
TP-005 | Recruit core founding team members | Hiring Manager & CEO | 2023-11-30 | In Progress | 50
TP-006 | Secure initial seed funding (target $500K) | CEO & CFO | 2023-12-15 | In Progress | 30
TP-007 | Design MVP prototype and user flow | UX/UI Designer & Dev Lead | 2023-11-20 | In Progress | 65
TP-008 | Set up legal structure and IP protection | Counsel & CFO | 2023-10-31 | Completed | 100
Overall Progress: |  |  |  |  | 52%